## Slide 1
Day 48 of 60
FFIC Approvals on time
Project Update Dashboard – Government Approvals
Project Objective: To secure various government approvals from various authorities
Project Time: 60 business days starting from April 1st
Project Risks:
  Resource unavailability next week may cause delays if alternate resource is not made available
  Budget is exhausted by $6200 More finances may be needed next week
Project Updates:
  FFIC approvals are on time as per the plan
  Approved documents heading to verification office for sign off
  5 of 8 tasks assigned to this week were completed
  3 tasks from this week and 4 tasks remaining are to be completed next week
Next Steps:
  Seek alternative resource for next week
  Complete 7 tasks by next week
Notes: SoliD is a new arm of a large global financial services firm targeting teens and millennials. The new platform and associated services are meant to appeal to the youth market by being low cost, having low barrier of entry, and super simple to use.

## Slide 2
Iteration 4
Next Product Release: Tomorrow
Project Update Dashboard – Mobile App
Project Objective: To develop a mobile app for potential and existing customers of SoliD
Project Time: Iteration 4 is completed and is bound to release tomorrow as per the plan. Iteration 5 will start after the user feedback from beta users
Project Updates:
  Bugs and issues are fixed from last release
  Positive feedback from beta users
  with product owner’s approval, iteration 4 will go live tomorrow
Project Risks:
  No known risks by the end of iteration 4 completion
Project Next Steps:
  Iteration 5 starts day after the release of iteration 4
  Beta users to try out the iteration 4
  Extension of product to regular user base
  Keep monitoring the bug reports by beta users for iteration 4 till the release of iteration 5